Meeting minutes –

Destinační management turistických lokalit regionu Hranicko a Dolina Małej Panwi

Date:		Friday 10th October 2008

Place: 		Hranice, Rozvojové partnerství office

Participants:	Jan Balek, Marcela Tomášová, Jana Černá, Konrad Waclawczyk, Franciszek Klimas, Michaela Randáčková

Agenda of the meeting:

- Management team, roles in the team

- Preliminary expenses

- Project schedule adjustment

- Budget, cash flow

- Regular meetings, type of communication

- Jan Balek took the introductory word, welcomed all the participants. The project management team was introduce: M. R. – project manager, Marcela Tomášová – financial manager, Jan Balek – supervisor, project manager from Polish side is not known yet; the selection procedure starts on Monday 13. 10. 2008 and according to polish law, it takes min. 1 month. Until the project manager is nominated, Konrad Waclawczyk is the contact person in Kolonowskie and Adam Wójtowicz in Zawadzkie.

- Project schedule – the new proposal of project schedule is attachment to the minutes; first activity of the project was guide service in Hranice city; the proposal of information leaflet about the project should be prepared in October 2008, leaflet is double-language (Czech – Polish), proposal is prepared by LP (“leader partner”) and sent to partners for agreement (budget is 500 EUR)

- Budget – announcement about change in the project budget - Hranice part of personal expenses 01.01 will be “moved” to External services 04.07 (others).

- Cash flow – adapted by Marcela Tomášová

- Regular contact between both project managers will be via e-mail and via Skype (M.R. Skype name is: mischarandackova, Marcela Tomášková Skype name is: marcela.tomasova1). As soon as the polish project manager is nominated, send his/her contacts to LP.

- A.o.b. - none