Meeting minutes, 4th December, 2008 in Hranice

Attendants:	Ania Szaton (Kolonowskie), Konrad Waclawczyk (Kolonowskie), Janusz Szampera (Zawadzkie), Marcela Tomášová (Hranická rozvojová agentura), Jan Balek (Hranická rozvojová agentura), Michaela Randáčková (Hranická rozvojová agentura)

Place:		Hranická rozvojová agentura office, Hranice

Agenda:	-    budget, promotion materials

- Regiontour fair in Brno (January 2009)

- First monitoring period, reports

- Next visit

1. Double-language leaflet – proposal send to Ania, Konrad and Janusz, polish partner will print out their part from their budget. Current proposal is not final, the map of Poland on the back side will be changed.

Leaflet “Hranicko” will be print out in Czech and Polish language; polish partner will make their own leaflet of region Dolina Małej Panwi and again make both languages version. These leaflets are special prepared for the RGT Fair in Brno 2009.

2. Regiontour Fair Brno – polish partner (Ania, Konrad, Janusz) will present their region in Brno 16th 2009. The next fair is planned in 2010 in Opole. There was a proposal to take part in the fair in Wroclaw in May 2009. This fair is much popular, more prestigious and much more visitors from abroad come there. We have to discuss that at the beginning next year, Janusz finds out when exactly the fair is and what are the conditions.

3. First monitoring period – we closed our first monitoring period 30th November and the report should be finalized till the end of December. There is a small problem with Christmas holidays and the deadline to handover it to our control authority is 22nd December 2008. Another problem is with system Benefit7 which is not prepared yet and we cannot do these reports in the system. Till the end of this week we will get the standpoint from our control authority how we should proceed further. Ania should find out if polish partner´s control authority is also in Olomouc.

4. Next visit – next meeting of the project partners is planned in Brno, during RGT. Visit of Czech partner in Poland will be according to the schedule activities or as necessary.